## 8_14 2014
PPD - as of 8/19/14
PC | Pub # | Group | New Edition/New Publication/Annual | Publication | Binding | Approx. Pages | Approx. Chapters | Series Template | Complexity | planning stage | first chapter(s) due | Half-way point | chapters in edit stage | Mrkting material review | 1st Set of Chapters Due Production | 2nd Set of Chapters Due Production/Marketing material review & cover | Final Chapters Due Production | Front/Back Matter to Production& indexing--need week before this date | Front/Back Matter to Production& indexing | Cenveo close | To Printer | Due from Printer | Arrived | Revenue Budgeted | Budgeted Revenue
3 | 4380005 | PC | New Edition | Commercial Property Coverage Guide, 5th Edition | Perfect |  |  | Coverage Guide | Medium | [5 empty] | 2012-11-01 | 2012-12-01 | 2012-12-15 |  |  |  | 2014-01-22 | 2013-02-15 | 2013-02-13 | March
4 | 1780013 | TF | Annual | 2013 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Heavy | [5 empty] | 2012-11-20 | 250 by 12/1/12 | 2012-12-10 |  |  |  | 2013-02-10 | 2013-03-04 | 2013-03-04 | April | April
4 | 1790013 | Training | New Edition | GBDS Course Handbook | Spiral | 500 | 19 | GBDS training layout | Light | [5 empty] | 2013-01-15 | 2013-02-01 | 2013-02-25 |  |  |  | 2013-03-05 | 2013-04-05 | 2013-03-22 | may be later due to spiral binding | Training
36 | 1780013 | TF | Annual | 2013 Field Guide to Financial Planning* | Perfect | 560 |  | Field Guide - 2 color | Medium | [5 empty] | 2013-02-05 | 2013-02-12 | 2013-03-05 |  |  |  | 2013-03-26 | 2013-04-15 | 2013-04-15 | April | April
6 | 2850016 | T-T | New Edition | Tools & Techniques of Estate Planning (Leimberg Library) 16th edition*** | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-01-20 | 2013-03-28 | 2013-04-08 |  |  |  | 2013-04-16 | 2013-05-12 | 2013-05-07 | June | June
3 | 4360010 | PC | New Edition | CGL Coverage Guide 10th Edition | Perfect | 525 |  | Coverage Guide | Light | [5 empty] | 2013-03-01 | 2013-03-15 | 2013-03-25 |  |  |  | 2013-04-05 | 2013-05-01 | 2013-04-26 | June/may be free | June
37 | Online Supplement | TF | Online Only | Healthcare Reform Facts | Perfect | 10 |  | Tax Facts | Light | [5 empty] | 2013-04-15 | [6 empty] | Posted when received | 2013-05-10 | November | No Revenue
6 | 2710013 | TT | New Edition | Tools & Techniques of Employee *** Benefits/Retirement Planning (Leimberg Library) 13th edition | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-02-23 | 2013-03-07 | 2013-04-08 |  |  |  | 2013-05-01 | 2013-05-24 | 2013-05-22 | June | June
3 | 2590000 | PC | New Publication | Guide to Captives and Alternative Risk Financing | Perfect | 350 | 82 | Modified Coverage Guide | Heavy | [5 empty] | 2013-01-25 | 2013-03-08 | 2013-04-05 |  |  |  | 2013-05-10 | 2013-06-07 | 2013-05-29 | June | June
41 | 9110000U | T-T | Rev. 1st Ed. | Principles of Estate Planning Supplement (production inhosue) | Perfect | 650 | 29 + 6 App. | Academic | Heavy | [5 empty] | 2013-07-01 | 2013-07-10 | 2013-07-15 |  |  |  | 2013-07-30 | 2013-08-31 | 2013-08-14
32 | 2920014 | TF | Annual | 2015 Tax Facts on Insurance | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2920014 | TF | Annual | 2015 Tax Facts on Employee Benefits | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2930014 | TF | Annual | 2014 Tax Facts on Investments | Perfect | 700 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
37 | 2990002 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 250 |  | Tax Facts | Simple | [5 empty] | 2013-08-09 | 2013-08-12 | 2014-08-14 |  |  |  | 2014-08-29 | 2014-09-21 | 2014-09-18 |  | October
40 | 3270000 | AG | New Edition | Advisor's Guide to 401(k) Plans | Perfect | 450 | 13 |  | Simple | [12 empty] | 2014-01-15 | 2014-01-07 | June | June
Advisor's Guide to Real Estate |  |  |  | Advisors Guide to Real Estate | [10 empty] | 2014-03-17 | 2014-03-24 | 2014-03-24 |  | 2014-03-30 | 2014-04-09 | 2014-04-09 | 2014-05-05 | may
40 | 2830004 | AG | New Edition | Advisor's Guide to Annuities, 4th Edition | Perfect | 325 | 14 |  | Simple | needs url |  |  | all |  | 41723 | 41729 | 4/15/2014 what's back from cenveo? | done | 2014-04-18 | 2014-04-24 | 2014-04-24 | 2014-05-24 | june | ? | September | moved up from July
3 | 4400005 | PC | New Edition | Homeowners CG, 5th Edition | Perfect | 500 | 16 -5 Appendices |  | Simple |  |  |  | all but index to cenveo |  | 41713 | 41747 | 41779 | 41774 | 41782 | 41786 | 5/27/2014-late, not a crisis | 41815 | august | December | December
|  |  | New Edition | Personal Auto CG, 3rd Edition (or alternative) |  |  |  |  | Simple | david & katherine | eric stuff done | david working on | all to Cenveo already |  | 41774 | 41788 | 41802 | 41802 | 41810 | 41819 | 41820 | 41850 | november-august?
|  |  | New | Homebased Business Coverage Guide | [6 empty] | 2014-07-01 |  | edited, all to cenveo, fm going today |  | 2014-07-15 | 2014-07-25 | 2014-08-01 | 2014-08-05 | 2014-08-11 | 2014-08-18 | 2014-08-18 | 2014-09-08 | august/september
|  |  |  | Building a Financial Services clientele(generic version) | [8 empty] | back from print |  | 2014-05-12 | 2014-05-21 | 2014-05-30 | 2014-05-27 | 2014-06-03 | 2014-06-10 | 2014-06-10 | 2014-07-08
|  |  |  | Critical Issues in CGL, 3rd edition | [8 empty] | at printer |  | 2014-06-13 | 2014-06-27 | 2014-07-15 | 2014-07-11 | 2014-07-18 | 2014-07-21 | 2014-07-21 | 2014-08-15 | august
|  |  | New | Construction Defects Coverage Guide-Zalma | [8 empty] | through chapter 9 back from cenveo | diana indexing | 2014-07-01 | 2014-07-18 | 2014-08-08 | 2014-08-03 | 2014-08-12 | 2014-08-19 | 2014-08-19 | 2014-09-09 | september
|  |  | New | Insurance Claims: A Comprehensive Guide-Zalma | [8 empty] | back from cenveo |  | 2014-07-01 | 2014-07-18 | 2014-08-08 | 2014-08-03 | 2014-08-12 | 2014-08-19 | 2014-08-19 | 2014-09-09 | september
|  |  | New | Mold Claims Coverage Guide-Zalma | [8 empty] | rest should be back from cenveo this week | being indexed | 2014-07-18 | 2014-08-08 | 2014-08-29 | 2014-08-27 | 2014-09-05 | 2014-09-30 | 2014-09-30 | 2014-10-24 | september
|  |  |  | Advisors Guide to Long-term Care | [5 empty] | ahead of schedule;Mike on chapters 19-20 & sales guide |  |  | most to cenveo, mike indexing |  | 2014-07-01 | 2014-07-18 | 2014-08-08 | 2014-08-03 | 2014-08-12 | 2014-08-19 | 2014-08-19 | 2014-09-09 | september
6 | 2740003 | T-T | New Edition | Tools & Techniques of Income Tax Planning, 4th Edition INSTRUCTOR MATERIALS | Perfect | 350 | 36 - 7 appendices |  | Simple | all chapter s assigned | 1/3 in | 18 chapters to go to cenveo now | gone to plan b, needs updated rates. |  | 2014-07-15 | 2014-08-01 | 2014-08-14 | 2014-08-11 | 2014-08-18 | 2014-08-20 | 2014-08-20 | 2014-09-12 | september | TBD | December
6 | 2500003 | T-T | New Edition | Tools & Techniques of Charitable Planning, 3rd edition INSTRUCTOR MATERIALS | Perfect | 400 | 26 - 12 appendices |  | Simple | all assigned | most chapters in |  | back from cenveo, indexing | will go early | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-08-25 | 2014-09-15 | september | subject to author arrangements | Replaces Real Estate
32 | TBD | TF | New Publication | Retirement Planning Facts | Perfect | 350 | 200 Q-As |  | Simple | TOC created | lou ritchie- rosalie-1st due in 7/15 |  | 13 back from rosalie |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-08-25 | 2014-09-15 | september | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Standard | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  | to print |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-07-28 | 2014-09-29 | october | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Mass Mutual | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  | closing |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-07-28 | 2014-09-29 | october | December | December
|  |  | New/Revised Edition | T-T Risk Management & Insurance, 2nd Edition |  |  |  |  | Simple | all assigned | 2014-06-01 |  | progressing | BEHIND | 2014-07-07 | 2014-07-22 | 2014-08-12 | 2014-08-12 | 2014-08-20 | 2014-09-01 | 2014-09-01 | 2014-10-01 | october
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner Northwestern | Spiral | 192 |  | Calendar | Simple | connie & tosha- custom |  |  | to cenveo; waiting on nw |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-07-28 | 2014-09-29 | october | December | December
|  |  |  | 2015 Health Savings Accounts Facts | [5 empty] | Mike |  |  | rest to cenveo this week, should have proofs end of week on 1st batch. |  | 2014-07-14 | 2014-07-28 | 2014-08-11 | 2014-08-13 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-28 | november
|  |  | New Edition | 2015 Healthcare Reform Facts | Perfect | 400 | 11 - 10 Appendices |  | Simple | outsourced to Mike Thomas | al writes |  | all in |  | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-13 | 2014-08-20 | 2014-08-22 | 2014-08-22 | 2014-09-15 | october | December | December
32 | 2920015 | TF | Annual-packaged together | Tax Facts on Insurance | Perfect | 860 | Plus Appendices |  | Simple | Rick | global village does cd's susan & connie | mid august need page count and quantities | progressing |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-20 | 2014-10-21 | 2014-11-17 | november
32 | 2920015 | TF | Annual-packaged together | Tax Facts on Employee Benefits | Perfect | 860 | Plus Appendices |  | Simple | Rick |  |  | progressing |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-20 | 2014-10-21 | 2014-11-17 | november
32 | 2930015 | TF | Annual | 2015 Tax Facts on Investments | Perfect | 700 | Plus Appendices | Tax Facts | Simple | Rick |  |  | progressing |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-14 | 2014-10-15 | 2014-11-17 | november | December | December
32 | 3190015 | TF | New Publication | 2015 Tax Facts on Individuals & Small Business | Perfecgt | 500 | Plus Appendices | Tax Facts | Simple | Rick |  |  | progressing |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-14 | 2014-10-15 | 2014-11-17 | november | December | December
|  |  |  | Tax Facts CDs (2-1for Ins/EB & 1 for investments) | [5 empty] | susan/connie |  |  |  |  | 2014-08-15: when book ready; 2014-08-22: 2014-11-01; 2014-08-25: 2014-11-01; 2014-09-28: 2014-11-17 | november
31 | 3800015 | PC | Annual | 2015 Licensing, Countersignature and S.L Laws | Perfect | 912 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  | receiving files from states, reviewing |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-11-10 | 2014-12-09 | december |  | Not Budgeted
30 | 4180015 | PC | Annual | 2015 Cancellation and NonRenewal | Perfect | 784 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  | receiving files from states, reviewing |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-11-10 | 2014-12-09 | december
34 | 1170015 | TF | Annual | 2015 ERISA Facts | Perfect | 980 | 13 sections/9 appendices | Tax Facts | Simple | frank Bitzer. Mike - will get all at once | 8/27 - 5 weeks |  | on track |  | 2014-10-08 | 2014-10-15 | 2012-10-22 | 2014-10-23 | 2014-10-30 | 2014-11-14 | 2014-11-14 | 2014-12-12 | december
35 | 1790015 | TF | Annual | 2015 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Simple | rick/zipse |  |  | has outline of content delivery, will t/b with authors |  | 2014-10-15 | 250 by 10/30/14 | 2014-11-11 | 2014-11-07 | 2014-11-14 | 2014-11-25 | 2014-11-25 | 2014-12-16 | december
33 | 3160015 | TF | Annual | 2015 Social Security & Medicare Facts | Perfect | 485 |  | Tax Facts | Simple | mike & joe | needs more authors |  | has a lot of content from new authors |  | 2014-10-01 | 2014-10-15 | 2014-10-30 | 2014-11-04 | 2014-11-11 | 2014-11-19 | 2014-11-19 | 2014-12-17 | december
|  |  |  | Insurance Case Law digest | [5 empty] | Steven and victoria |  |  |  |  | 2014-09-12 | 2014-10-03 | 2014-10-24 | 2014-10-31 | 2014-11-06 | 2014-11-14 | 2014-11-14 | 2014-12-08 | december
33 |  | TF | Annual | 2015 SS/Medicare Planners | Folder |  |  | Brochure | Simple | joe stenken |  |  | have content from additional authors |  | 2014-11-21 |  |  |  | N/A | 2014-12-05 | 2014-12-05 | 2014-12-17 | december
|  |  |  | Tax Facts at a Glance | [5 empty] | connie |  |  |  |  | 2014-08-15: All when tax numbers ready; 2014-09-28: per tax numbers | no revenue
Online |  |  |  | Retirement Plan Service/partner with Advisys | [5 empty] | rick - prototype 4/22 |  |  | ADVISYS HAS |  | 2014-07-14: ONLINE ONLY; 2014-09-28: expected June release
Comments
6 | 2770011 | T-T | New Edition | Tools & Techniques of Financial Planning, 11th Edition |  |  |  |  | Simple | ? | [12 empty] | awaiting financials
|  |  | custom | NWM Custom - building a financial services clientele
|  |  | 200 | Supplement/companion to SS/Medicare Facts | [18 empty] | target 12/14
|  |  | 350 | State Specific Tax Facts Supplement | [18 empty] | Cline investigating
Healthcare reform update service
|  |  |  | COBRA Facts | [18 empty] | Rick K.
|  |  |  | FCSL Case Law Digest | [18 empty] | December 2015?
Other Projects
Tier IV FC&S
|  |  |  | Adding case law to FCSL and FCIN | Begin 10/13
|  |  | 2015 | field guide to financial planning
|  |  | 2015 | principles of Estate Planning Supplement (production inhosue)???'

## 4_25 2014 (3)
PPD - as of 4/25/14
PC | Pub # | Group | New Edition/New Publication/Annual | Publication | Binding | Approx. Pages | Approx. Chapters | Series Template | Complexity | planning stage | first chapter(s) due | Half-way point | chapters in edit stage | Mrkting material review | 1st Set of Chapters Due Production | 2nd Set of Chapters Due Production/Marketing material review & cover | Final Chapters Due Production | Front/Back Matter to Production& indexing--need week before this date | Front/Back Matter to Production& indexing | To Purchasing | Due from Printer | Arrived | Revenue Budgeted | Budgeted Revenue
3 | 4380005 | PC | New Edition | Commercial Property Coverage Guide, 5th Edition | Perfect |  |  | Coverage Guide | Medium | [5 empty] | 2012-11-01 | 2012-12-01 | 2012-12-15 |  |  | 2014-01-22 | 2013-02-15 | 2013-02-13 | March
4 | 1780013 | TF | Annual | 2013 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Heavy | [5 empty] | 2012-11-20 | 250 by 12/1/12 | 2012-12-10 |  |  | 2013-02-10 | 2013-03-04 | 2013-03-04 | April | April
4 | 1790013 | Training | New Edition | GBDS Course Handbook | Spiral | 500 | 19 | GBDS training layout | Light | [5 empty] | 2013-01-15 | 2013-02-01 | 2013-02-25 |  |  | 2013-03-05 | 2013-04-05 | 2013-03-22 | may be later due to spiral binding | Training
36 | 1780013 | TF | Annual | 2013 Field Guide to Financial Planning* | Perfect | 560 |  | Field Guide - 2 color | Medium | [5 empty] | 2013-02-05 | 2013-02-12 | 2013-03-05 |  |  | 2013-03-26 | 2013-04-15 | 2013-04-15 | April | April
6 | 2850016 | T-T | New Edition | Tools & Techniques of Estate Planning (Leimberg Library) 16th edition*** | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-01-20 | 2013-03-28 | 2013-04-08 |  |  | 2013-04-16 | 2013-05-12 | 2013-05-07 | June | June
3 | 4360010 | PC | New Edition | CGL Coverage Guide 10th Edition | Perfect | 525 |  | Coverage Guide | Light | [5 empty] | 2013-03-01 | 2013-03-15 | 2013-03-25 |  |  | 2013-04-05 | 2013-05-01 | 2013-04-26 | June/may be free | June
37 | Online Supplement | TF | Online Only | Healthcare Reform Facts | Perfect | 10 |  | Tax Facts | Light | [5 empty] | 2013-04-15 | [5 empty] | Posted when received | 2013-05-10 | November | No Revenue
6 | 2710013 | TT | New Edition | Tools & Techniques of Employee *** Benefits/Retirement Planning (Leimberg Library) 13th edition | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-02-23 | 2013-03-07 | 2013-04-08 |  |  | 2013-05-01 | 2013-05-24 | 2013-05-22 | June | June
3 | 2590000 | PC | New Publication | Guide to Captives and Alternative Risk Financing | Perfect | 350 | 82 | Modified Coverage Guide | Heavy | [5 empty] | 2013-01-25 | 2013-03-08 | 2013-04-05 |  |  | 2013-05-10 | 2013-06-07 | 2013-05-29 | June | June
41 | 9110000U | T-T | Rev. 1st Ed. | Principles of Estate Planning Supplement (production inhosue) | Perfect | 650 | 29 + 6 App. | Academic | Heavy | [5 empty] | 2013-07-01 | 2013-07-10 | 2013-07-15 |  |  | 2013-07-30 | 2013-08-31 | 2013-08-14
32 | 2920014 | TF | Annual | 2015 Tax Facts on Insurance | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2920014 | TF | Annual | 2015 Tax Facts on Employee Benefits | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2930014 | TF | Annual | 2014 Tax Facts on Investments | Perfect | 700 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
37 | 2990002 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 250 |  | Tax Facts | Simple | [5 empty] | 2013-08-09 | 2013-08-12 | 2014-08-14 |  |  | 2014-08-29 | 2014-09-21 | 2014-09-18 |  | October
40 | 3270000 | AG | New Edition | Advisor's Guide to 401(k) Plans | Perfect | 450 | 13 |  | Simple | [11 empty] | 2014-01-15 | 2014-01-07 | June | June
Advisor's Guide to Real Estate |  |  |  | Advisors Guide to Real Estate | [10 empty] | 2014-03-17 | 2014-03-24 | 2014-03-24 |  | 2014-03-30 | 2014-04-09 | 2014-05-05
40 | 2830004 | AG | New Edition | Advisor's Guide to Annuities, 4th Edition | Perfect | 325 | 14 |  | Simple |  |  |  | all |  | 2014-03-25 | 2014-03-31 | 4/15/2014 what's back from cenveo? | has this been done yet? | 2014-04-18 | 2014-04-24 | 2014-05-24 |  | ? | September | moved up from July
3 | 4400005 | PC | New Edition | Homeowners CG, 5th Edition | Perfect | 500 | 16 -5 Appendices |  | Simple |  |  |  | 1-9 edited, 10-11 just to emily 5/2 |  | 2014-03-15 | 2014-04-18 | 2014-05-20 | 2014-05-15 | 2014-05-23 | 2014-05-27 | 2014-06-25 |  | December | December
|  |  |  | Building a Financial Services clientele(generic version) | [10 empty] | 2014-05-12 | 2014-05-21 | 2014-05-30 | 2014-05-27 | 2014-06-03 | 2014-06-10 | 2014-07-08
|  |  |  | Critical Issues in CGL, 3rd edition | [5 empty] | Katherine working on authors |  |  |  |  | 2014-06-13 | 2014-06-27 | 2014-07-15 | 2014-07-11 | 2014-07-18 | 2014-07-21 | 2014-08-15
|  |  |  | Advisors Guide to Long-term Care Insurance | [10 empty] | 2014-07-01 | 2014-07-18 | 2014-08-08 | 2014-08-03 | 2014-08-12 | 2014-08-19 | 2014-09-09
6 | 2740003 | T-T | New Edition | Tools & Techniques of Income Tax Planning, 4th Edition | Perfect | 350 | 36 - 7 appendices |  | Simple | needs 1 more author | chapter 4 ready to go- call m j |  | 6/15 |  | 2014-07-15 | 2014-08-01 | 2014-08-14 | 2014-08-11 | 2014-08-18 | 2014-08-20 | 2014-09-12 |  | TBD | December
6 | 2500003 | T-T | New Edition | Tools & Techniques of Charitable Planning, 3rd edition | Perfect | 400 | 26 - 12 appendices |  | Simple | remaining 5 chapters assigned? | 1 chapter in |  | 5/15 |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 |  | subject to author arrangements | Replaces Real Estate
32 | TBD | TF | New Publication | Retirement Planning Facts | Perfect | 350 | 200 Q-As |  | Simple | TOC created | lou ritchie- rosalie |  |  |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 |  | December | December
37 | 2990015 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 400 | 11 - 10 Appendices |  | Simple | outsourced to Mike Thomas | al writes |  |  |  | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-13 | 2014-08-20 | 2014-08-22 | 2014-09-15 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Standard | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Mass Mutual | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner Northwestern | Spiral | 192 |  | Calendar | Simple | connie & tosha- custom |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
32 | 2920015 | TF | Annual | Tax Facts on Insurance | Perfect | 860 | Plus Appendices |  | Simple | Rick | global village does cd's susan & connie |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17
32 | 2920015 | TF | Annual | Tax Facts on Employee Benefits | Perfect | 860 | Plus Appendices |  | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17
32 | 2930015 | TF | Annual | 2015 Tax Facts on Investments | Perfect | 700 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 |  | December | December
32 | 3190015 | TF | New Publication | 2015 Tax Facts on Individuals & Small Business | Perfecgt | 500 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 |  | December | December
|  |  |  | Tax Facts CDs (2-1for Ins/EB & 1 for investments) | [5 empty] | susan/connie | [8 empty] | when book ready | 2014-11-01 | 2014-11-17
31 | 3800015 | PC | Annual | 2015 Licensing, Countersignature and S.L Laws | Perfect | 912 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09 |  |  | Not Budgeted
30 | 4180015 | PC | Annual | 2015 Cancellation and NonRenewal | Perfect | 784 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09
34 | 1170015 | TF | Annual | 2015 ERISA Facts | Perfect | 980 | 13 sections/9 appendices | Tax Facts | Simple | frank Bitzer? Needs author-rick to call |  |  |  |  | 2014-10-08 | 2014-10-15 | 2012-10-22 | 2014-10-23 | 2014-10-30 | 2014-11-14 | 2014-12-12
35 | 1790015 | TF | Annual | 2015 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Simple | rick |  |  | 9/15 |  | 2014-10-15 | 250 by 10/30/14 | 2014-11-11 | 2014-11-07 | 2014-11-14 | 2014-11-25 | 2014-12-16
33 | 3160015 | TF | Annual | 2015 Social Security & Medicare Facts | Perfect | 485 |  | Tax Facts | Simple | mike & joe |  |  | 9/1 |  | 2014-10-01 | 2014-10-15 | 2014-10-30 | 2014-11-04 | 2014-11-11 | 2014-11-19 | 2014-12-17
33 |  | TF | Annual | 2015 SS/Medicare Planners | Folder |  |  | Brochure | Simple | joe stenken |  |  |  |  | 2014-10-01: 2014-11-21; 2014-11-11: N/A; 2014-11-19: 2014-12-05; 2014-12-17: 2014-12-17
|  |  |  | Tax Facts at a Glance | [5 empty] | connie |  |  |  |  | 2014-11-11: All when tax numbers ready; 2014-12-17: per tax numbers
2015 Health Savings Accounts Facts
3 | 4450003 | PC | New Edition | Personal Auto CG, 3rd Edition (or alternative) |  |  |  |  | Simple | david & katherine | eric stuff done | david working on | all |  | 2014-12-17: TBD
6 | TBD | T-t | New/Revised Edition | T-T Risk Management & Insurance, 2nd Edition |  |  |  |  | Simple | jason - P&C to be assigned inside |  |  |  |  | 2014-12-17: TBD
Under Discussion | [21 empty] | Comments
6 | 2770011 | T-T | New Edition | Tools & Techniques of Financial Planning, 11th Edition |  |  |  |  | Simple | ? | [11 empty] | awaiting financials
|  |  | custom | NWM Custom - building a financial services clientele
|  |  | 200 | Supplement/companion to SS/Medicare Facts | [17 empty] | target 12/14
|  |  | 350 | State Specific Tax Facts Supplement | [17 empty] | Cline investigating
|  |  | Online | Retirement Plan Service/partner with Advisys | [5 empty] | rick - protptype 4/22 | [11 empty] | Aim to release in July
Healthcare reform update service
|  |  |  | COBRA Facts | [17 empty] | Rick K.
|  |  |  | FCSL Case Law Digest | [17 empty] | December 2015?
Other Projects
Tier IV FC&S
|  |  |  | Adding case law to FCSL and FCIN | Begin 10/13

## 4_25 2014 budget month
PPD - as of 4/25/14
PC | Pub # | Group | New Edition/New Publication/Annual | Publication | Binding | Approx. Pages | Approx. Chapters | Series Template | Complexity | planning stage | first chapter(s) due | Half-way point | chapters in edit stage | Mrkting material review | 1st Set of Chapters Due Production | 2nd Set of Chapters Due Production/Marketing material review & cover | Final Chapters Due Production | Front/Back Matter to Production& indexing--need week before this date | Front/Back Matter to Production& indexing | To Purchasing | Due from Printer | Arrived | Revenue Budgeted | Budgeted Revenue
3 | 4380005 | PC | New Edition | Commercial Property Coverage Guide, 5th Edition | Perfect |  |  | Coverage Guide | Medium | [5 empty] | 2012-11-01 | 2012-12-01 | 2012-12-15 |  |  | 2014-01-22 | 2013-02-15 | 2013-02-13 | March
4 | 1780013 | TF | Annual | 2013 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Heavy | [5 empty] | 2012-11-20 | 250 by 12/1/12 | 2012-12-10 |  |  | 2013-02-10 | 2013-03-04 | 2013-03-04 | April | April
4 | 1790013 | Training | New Edition | GBDS Course Handbook | Spiral | 500 | 19 | GBDS training layout | Light | [5 empty] | 2013-01-15 | 2013-02-01 | 2013-02-25 |  |  | 2013-03-05 | 2013-04-05 | 2013-03-22 | may be later due to spiral binding | Training
36 | 1780013 | TF | Annual | 2013 Field Guide to Financial Planning* | Perfect | 560 |  | Field Guide - 2 color | Medium | [5 empty] | 2013-02-05 | 2013-02-12 | 2013-03-05 |  |  | 2013-03-26 | 2013-04-15 | 2013-04-15 | April | April
6 | 2850016 | T-T | New Edition | Tools & Techniques of Estate Planning (Leimberg Library) 16th edition*** | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-01-20 | 2013-03-28 | 2013-04-08 |  |  | 2013-04-16 | 2013-05-12 | 2013-05-07 | June | June
3 | 4360010 | PC | New Edition | CGL Coverage Guide 10th Edition | Perfect | 525 |  | Coverage Guide | Light | [5 empty] | 2013-03-01 | 2013-03-15 | 2013-03-25 |  |  | 2013-04-05 | 2013-05-01 | 2013-04-26 | June/may be free | June
37 | Online Supplement | TF | Online Only | Healthcare Reform Facts | Perfect | 10 |  | Tax Facts | Light | [5 empty] | 2013-04-15 | [5 empty] | Posted when received | 2013-05-10 | November | No Revenue
6 | 2710013 | TT | New Edition | Tools & Techniques of Employee *** Benefits/Retirement Planning (Leimberg Library) 13th edition | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-02-23 | 2013-03-07 | 2013-04-08 |  |  | 2013-05-01 | 2013-05-24 | 2013-05-22 | June | June
3 | 2590000 | PC | New Publication | Guide to Captives and Alternative Risk Financing | Perfect | 350 | 82 | Modified Coverage Guide | Heavy | [5 empty] | 2013-01-25 | 2013-03-08 | 2013-04-05 |  |  | 2013-05-10 | 2013-06-07 | 2013-05-29 | June | June
41 | 9110000U | T-T | Rev. 1st Ed. | Principles of Estate Planning Supplement (production inhosue) | Perfect | 650 | 29 + 6 App. | Academic | Heavy | [5 empty] | 2013-07-01 | 2013-07-10 | 2013-07-15 |  |  | 2013-07-30 | 2013-08-31 | 2013-08-14
32 | 2920014 | TF | Annual | 2015 Tax Facts on Insurance | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2920014 | TF | Annual | 2015 Tax Facts on Employee Benefits | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2930014 | TF | Annual | 2014 Tax Facts on Investments | Perfect | 700 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
37 | 2990002 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 250 |  | Tax Facts | Simple | [5 empty] | 2013-08-09 | 2013-08-12 | 2014-08-14 |  |  | 2014-08-29 | 2014-09-21 | 2014-09-18 |  | October
40 | 3270000 | AG | New Edition | Advisor's Guide to 401(k) Plans | Perfect | 450 | 13 |  | Simple | [11 empty] | 2014-01-15 | 2014-01-07 | June | June
Advisor's Guide to Real Estate |  |  |  | Advisors Guide to Real Estate | [10 empty] | 2014-03-17 | 2014-03-24 | 2014-03-24 |  | 2014-03-30 | 2014-04-09 | 2014-05-05 | may
40 | 2830004 | AG | New Edition | Advisor's Guide to Annuities, 4th Edition | Perfect | 325 | 14 |  | Simple |  |  |  | all |  | 2014-03-25 | 2014-03-31 | 4/15/2014 what's back from cenveo? | has this been done yet? | 2014-04-18 | 2014-04-24 | 2014-05-24 | june | ? | September | moved up from July
3 | 4400005 | PC | New Edition | Homeowners CG, 5th Edition | Perfect | 500 | 16 -5 Appendices |  | Simple |  |  |  | 1-9 edited, 10-11 just to emily 5/2 |  | 2014-03-15 | 2014-04-18 | 2014-05-20 | 2014-05-15 | 2014-05-23 | 2014-05-27 | 2014-06-25 | august | December | December
|  |  |  | Building a Financial Services clientele(generic version) | [10 empty] | 2014-05-12 | 2014-05-21 | 2014-05-30 | 2014-05-27 | 2014-06-03 | 2014-06-10 | 2014-07-08
|  |  |  | Critical Issues in CGL, 3rd edition | [5 empty] | Katherine working on authors |  |  |  |  | 2014-06-13 | 2014-06-27 | 2014-07-15 | 2014-07-11 | 2014-07-18 | 2014-07-21 | 2014-08-15 | august
|  |  |  | Advisors Guide to Long-term Care Insurance | [10 empty] | 2014-07-01 | 2014-07-18 | 2014-08-08 | 2014-08-03 | 2014-08-12 | 2014-08-19 | 2014-09-09 | september
6 | 2740003 | T-T | New Edition | Tools & Techniques of Income Tax Planning, 4th Edition | Perfect | 350 | 36 - 7 appendices |  | Simple | needs 1 more author | chapter 4 ready to go- call m j |  | 6/15 |  | 2014-07-15 | 2014-08-01 | 2014-08-14 | 2014-08-11 | 2014-08-18 | 2014-08-20 | 2014-09-12 | september | TBD | December
6 | 2500003 | T-T | New Edition | Tools & Techniques of Charitable Planning, 3rd edition | Perfect | 400 | 26 - 12 appendices |  | Simple | remaining 5 chapters assigned? | 1 chapter in |  | 5/15 |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 | september | subject to author arrangements | Replaces Real Estate
32 | TBD | TF | New Publication | Retirement Planning Facts | Perfect | 350 | 200 Q-As |  | Simple | TOC created | lou ritchie- rosalie |  |  |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 | september | December | December
37 | 2990015 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 400 | 11 - 10 Appendices |  | Simple | outsourced to Mike Thomas | al writes |  |  |  | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-13 | 2014-08-20 | 2014-08-22 | 2014-09-15 | september | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Standard | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 | october | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Mass Mutual | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 | october | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner Northwestern | Spiral | 192 |  | Calendar | Simple | connie & tosha- custom |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 | october | December | December
32 | 2920015 | TF | Annual | Tax Facts on Insurance | Perfect | 860 | Plus Appendices |  | Simple | Rick | global village does cd's susan & connie |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 | november
32 | 2920015 | TF | Annual | Tax Facts on Employee Benefits | Perfect | 860 | Plus Appendices |  | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 | november
32 | 2930015 | TF | Annual | 2015 Tax Facts on Investments | Perfect | 700 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 | november | December | December
32 | 3190015 | TF | New Publication | 2015 Tax Facts on Individuals & Small Business | Perfecgt | 500 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-09-17 | 2014-09-24 | remainder by 10/7/2014 | 2014-10-03 | 2014-10-10 | 2014-10-15 | 2014-11-17 | november | December | December
|  |  |  | Tax Facts CDs (2-1for Ins/EB & 1 for investments) | [5 empty] | susan/connie | [8 empty] | when book ready | 2014-11-01 | 2014-11-17 | november
31 | 3800015 | PC | Annual | 2015 Licensing, Countersignature and S.L Laws | Perfect | 912 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09 | december |  | Not Budgeted
30 | 4180015 | PC | Annual | 2015 Cancellation and NonRenewal | Perfect | 784 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09 | december
34 | 1170015 | TF | Annual | 2015 ERISA Facts | Perfect | 980 | 13 sections/9 appendices | Tax Facts | Simple | frank Bitzer? Needs author-rick to call |  |  |  |  | 2014-10-08 | 2014-10-15 | 2012-10-22 | 2014-10-23 | 2014-10-30 | 2014-11-14 | 2014-12-12 | december
35 | 1790015 | TF | Annual | 2015 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Simple | rick |  |  | 9/15 |  | 2014-10-15 | 250 by 10/30/14 | 2014-11-11 | 2014-11-07 | 2014-11-14 | 2014-11-25 | 2014-12-16 | december
33 | 3160015 | TF | Annual | 2015 Social Security & Medicare Facts | Perfect | 485 |  | Tax Facts | Simple | mike & joe |  |  | 9/1 |  | 2014-10-01 | 2014-10-15 | 2014-10-30 | 2014-11-04 | 2014-11-11 | 2014-11-19 | 2014-12-17 | december
33 |  | TF | Annual | 2015 SS/Medicare Planners | Folder |  |  | Brochure | Simple | joe stenken |  |  |  |  | 2014-10-01: 2014-11-21; 2014-11-11: N/A; 2014-11-19: 2014-12-05; 2014-12-17: 2014-12-17 | december
|  |  |  | Tax Facts at a Glance | [5 empty] | connie |  |  |  |  | 2014-11-11: All when tax numbers ready; 2014-12-17: per tax numbers | no revenue
|  |  |  | 2015 Health Savings Accounts Facts | [17 empty] | november
3 | 4450003 | PC | New Edition | Personal Auto CG, 3rd Edition (or alternative) |  |  |  |  | Simple | david & katherine | eric stuff done | david working on | all |  | 2014-12-17: TBD | november
6 | TBD | T-t | New/Revised Edition | T-T Risk Management & Insurance, 2nd Edition |  |  |  |  | Simple | jason - P&C to be assigned inside |  |  |  |  | 2014-12-17: TBD | october
Under Discussion | [21 empty] | Comments
6 | 2770011 | T-T | New Edition | Tools & Techniques of Financial Planning, 11th Edition |  |  |  |  | Simple | ? | [11 empty] | awaiting financials
|  |  | custom | NWM Custom - building a financial services clientele
|  |  | 200 | Supplement/companion to SS/Medicare Facts | [17 empty] | target 12/14
|  |  | 350 | State Specific Tax Facts Supplement | [17 empty] | Cline investigating
|  |  | Online | Retirement Plan Service/partner with Advisys | [5 empty] | rick - protptype 4/22 | [11 empty] | Aim to release in July
Healthcare reform update service
|  |  |  | COBRA Facts | [17 empty] | Rick K.
|  |  |  | FCSL Case Law Digest | [17 empty] | December 2015?
Other Projects
Tier IV FC&S
|  |  |  | Adding case law to FCSL and FCIN | Begin 10/13

## 2014
PPD - as of3/4/14
PC | Pub # | Group | New Edition/New Publication/Annual | Publication | Binding | Approx. Pages | Approx. Chapters | Series Template | Complexity | planning stage | first chapter(s) due | Half-way point | chapters in edit stage | Mrkting material review | 1st Set of Chapters Due Production | 2nd Set of Chapters Due Production/Marketing material review & cover | Final Chapters Due Production | Front/Back Matter to Production& indexing--need week before this date | Front/Back Matter to Production& indexing | To Purchasing | Due from Printer | Arrived | Revenue Budgeted | Budgeted Revenue
3 | 4380005 | PC | New Edition | Commercial Property Coverage Guide, 5th Edition | Perfect |  |  | Coverage Guide | Medium | [5 empty] | 2012-11-01 | 2012-12-01 | 2012-12-15 |  |  | 2014-01-22 | 2013-02-15 | 2013-02-13 | March
4 | 1780013 | TF | Annual | 2013 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Heavy | [5 empty] | 2012-11-20 | 250 by 12/1/12 | 2012-12-10 |  |  | 2013-02-10 | 2013-03-04 | 2013-03-04 | April | April
4 | 1790013 | Training | New Edition | GBDS Course Handbook | Spiral | 500 | 19 | GBDS training layout | Light | [5 empty] | 2013-01-15 | 2013-02-01 | 2013-02-25 |  |  | 2013-03-05 | 2013-04-05 | 2013-03-22 | may be later due to spiral binding | Training
36 | 1780013 | TF | Annual | 2013 Field Guide to Financial Planning* | Perfect | 560 |  | Field Guide - 2 color | Medium | [5 empty] | 2013-02-05 | 2013-02-12 | 2013-03-05 |  |  | 2013-03-26 | 2013-04-15 | 2013-04-15 | April | April
6 | 2850016 | T-T | New Edition | Tools & Techniques of Estate Planning (Leimberg Library) 16th edition*** | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-01-20 | 2013-03-28 | 2013-04-08 |  |  | 2013-04-16 | 2013-05-12 | 2013-05-07 | June | June
3 | 4360010 | PC | New Edition | CGL Coverage Guide 10th Edition | Perfect | 525 |  | Coverage Guide | Light | [5 empty] | 2013-03-01 | 2013-03-15 | 2013-03-25 |  |  | 2013-04-05 | 2013-05-01 | 2013-04-26 | June/may be free | June
37 | Online Supplement | TF | Online Only | Healthcare Reform Facts | Perfect | 10 |  | Tax Facts | Light | [5 empty] | 2013-04-15 | [5 empty] | Posted when received | 2013-05-10 | November | No Revenue
6 | 2710013 | TT | New Edition | Tools & Techniques of Employee *** Benefits/Retirement Planning (Leimberg Library) 13th edition | Perfect |  |  | Tools & Techniques | Heavy | [5 empty] | 2013-02-23 | 2013-03-07 | 2013-04-08 |  |  | 2013-05-01 | 2013-05-24 | 2013-05-22 | June | June
3 | 2590000 | PC | New Publication | Guide to Captives and Alternative Risk Financing | Perfect | 350 | 82 | Modified Coverage Guide | Heavy | [5 empty] | 2013-01-25 | 2013-03-08 | 2013-04-05 |  |  | 2013-05-10 | 2013-06-07 | 2013-05-29 | June | June
41 | 9110000U | T-T | Rev. 1st Ed. | Principles of Estate Planning Supplement (production inhosue) | Perfect | 650 | 29 + 6 App. | Academic | Heavy | [5 empty] | 2013-07-01 | 2013-07-10 | 2013-07-15 |  |  | 2013-07-30 | 2013-08-31 | 2013-08-14
32 | 2920014 | TF | Annual | 2015 Tax Facts on Insurance | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2920014 | TF | Annual | 2015 Tax Facts on Employee Benefits | Perfect | 500-550 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
32 | 2930014 | TF | Annual | 2014 Tax Facts on Investments | Perfect | 700 | N/A | Tax Facts | Simple | [5 empty] | 2013-07-15 | 2013-07-25 | remainder by 8/1/13 |  |  | 2013-08-15 | 2013-09-18 | 2013-09-17 | November | November
37 | 2990002 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 250 |  | Tax Facts | Simple | [5 empty] | 2013-08-09 | 2013-08-12 | 2014-08-14 |  |  | 2014-08-29 | 2014-09-21 | 2014-09-18 |  | October
40 | 3270000 | AG | New Edition | Advisor's Guide to 401(k) Plans | Perfect | 450 | 13 |  | Simple | [11 empty] | 2014-01-15 | 2014-01-07 | June | June
36 | 1780014 | TF | Annual | 2014 Field Guide to Financial Planning | Perfect | 527 | 18 |  | Simple | [5 empty] | 2013-12-15 | 2014-01-07 | 2014-01-24 |  | 2014-01-29 | 2014-02-12 | 2014-03-12 | 2014-03-12 | September | September
6 | N/A | T-T | Supplement/online only | Supplement to Principles of Estate Planning, 1st Ed. Revised | Online |  |  |  |  | done | [10 empty] | 2014-03-14 | done | October | October
40 | TBD | AG | New Publication | Advisor's Guide to Real Estate | Perfect | 350 | 13 |  | Simple | x | x | x | x | x | 2014-03-17 | 3/242/2014 | 2014-03-24 |  | 2014-03-30 | 2014-04-09 | 2014-05-05 | at printer - ebokk ready end of week | December | December
40 | 2830004 | AG | New Edition | Advisor's Guide to Annuities, 4th Edition | Perfect | 325 | 14 |  | Simple |  |  |  | all |  | 2014-03-25 | 2014-03-31 | 4/15/2014 what's back from cenveo? | has this been done yet? | 2014-04-18 | 2014-04-24 | 2014-05-24 |  | ? | September | moved up from July
3 | 4400005 | PC | New Edition | Homeowners CG, 5th Edition | Perfect | 500 | 16 -5 Appendices |  | Simple |  |  |  | 1-8 edited |  | 2014-03-15 | 2014-04-18 | 2014-05-20 | 2014-05-15 | 2014-05-23 | 2014-05-27 | 2014-06-25 |  | December | December
6 | 2740003 | T-T | New Edition | Tools & Techniques of Income Tax Planning, 4th Edition | Perfect | 350 | 36 - 7 appendices |  | Simple | needs 1 more author | chapter 4 ready to go- call m j |  | 6/15 |  | 2014-07-15 | 2014-08-01 | 2014-08-14 | 2014-08-11 | 2014-08-18 | 2014-08-20 | 2014-09-12 |  | TBD | December
6 | 2500003 | T-T | New Edition | Tools & Techniques of Charitable Planning, 3rd edition | Perfect | 400 | 26 - 12 appendices |  | Simple | remaining 5 chapters assigned? | 1 chapter in |  | 5/15 |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 |  | subject to author arrangements | Replaces Real Estate
32 | TBD | TF | New Publication | Retirement Planning Facts | Perfect | 350 | 200 Q-As |  | Simple | TOC created | lou ritchie- jason |  |  |  | 2014-07-25 | 2014-08-06 | 8/19//14 | 2014-08-15 | 2014-08-22 | 2014-08-25 | 2014-09-15 |  | December | December
37 | 2990015 | TF | New Edition | 2015 Healthcare Reform Facts | Perfect | 400 | 11 - 10 Appendices |  | Simple | outsourced to Mike Thomas | al writes |  |  |  | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-13 | 2014-08-20 | 2014-08-22 | 2014-09-15 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Standard | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner - Mass Mutual | Spiral | 192 |  | Calendar | Simple | connie & tosha |  |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
8 | 1660014 | OCS | New Edition/Annual | OCS 2015 Planner Northwestern | Spiral | 192 |  | Calendar | Simple | connie & tosha- custom | global village does cd's susan & connie |  |  |  | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | N/A | 2014-07-28 | 2014-09-29 |  | December | December
32 | 2920015 | TF | Annual | Tax Facts on Insurance | Perfect | 860 | Plus Appendices |  | Simple | Rick |  |  |  |  | 2014-07-14 | 2014-07-23 | remainder by 8/1/14 | 2014-08-04 | 2014-08-11 | 2014-08-15 | 2014-09-10
32 | 2920015 | TF | Annual | Tax Facts on Employee Benefits | Perfect | 860 | Plus Appendices |  | Simple | Rick |  |  |  |  | 2014-07-14 | 2014-07-23 | remainder by 8/1/14 | 2014-08-04 | 2014-08-11 | 2014-08-15 | 2014-09-10
32 | 2930015 | TF | Annual | 2015 Tax Facts on Investments | Perfect | 700 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-07-14 | 2014-07-23 | remainder by 8/1/14 | 2014-08-04 | 2014-08-11 | 2014-08-15 | 2014-09-10 |  | December | December
32 | 3190015 | TF | New Publication | 2015 Tax Facts on Individuals & Small Business | Perfecgt | 500 | Plus Appendices | Tax Facts | Simple | Rick |  |  |  |  | 2014-07-14 | 2014-07-23 | remainder by 8/1/14 | 2014-08-04 | 2014-08-11 | 2014-08-15 | 2014-09-10 |  | December | December
31 | 3800015 | PC | Annual | 2015 Licensing, Countersignature and S.L Laws | Perfect | 912 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09 |  |  | Not Budgeted
30 | 4180015 | PC | Annual | 2015 Cancellation and NonRenewal | Perfect | 784 | 54 states/jur | PC Annuals | Simple |  | 2014-08-19 |  |  |  | 2014-09-30 | 18 by 10-10 | 2014-10-22 | 2014-10-28 | 2014-11-04 | 2014-11-10 | 2014-12-09
34 | 1170015 | TF | Annual | 2015 ERISA Facts | Perfect | 980 | 13 sections/9 appendices | Tax Facts | Simple | frank Bitzer? Needs author-rick to call |  |  |  |  | 2014-10-08 | 2014-10-15 | 2012-10-22 | 2014-10-23 | 2014-10-30 | 2014-11-14 | 2014-12-12
35 | 1790015 | TF | Annual | 2015 Field Guide to Estate Planning | Perfect | 625 |  | Field Guide - 4 color | Simple |  |  |  | 9/15 |  | 2014-10-15 | 250 by 10/30/14 | 2014-11-11 | 2014-11-07 | 2014-11-14 | 2014-11-25 | 2014-12-16
33 | 3160015 | TF | Annual | 2015 Social Security & Medicare Facts | Perfect | 485 |  | Tax Facts | Simple |  |  |  | 9/1 |  | 2014-10-01 | 2014-10-15 | 2014-10-30 | 2014-11-04 | 2014-11-11 | 2014-11-19 | 2014-12-17
33 |  | TF | Annual | 2015 SS/Medicare Planners | Folder |  |  | Brochure | Simple | joe stenken |  |  |  |  | 2014-10-01: 2014-11-21; 2014-11-11: N/A; 2014-11-19: 2014-12-05; 2014-12-17: 2014-12-17
3 | 4450003 | PC | New Edition | Personal Auto CG, 3rd Edition (or alternative) |  |  |  |  | Simple |  | eric stuff done | david working on | all |  | 2014-12-17: TBD
3 | 5050003 | PC | New Edition | Commercial General Liability, Critical Issues, 3rd Edition |  |  |  |  | Simple | Katherine working on authors |  |  |  |  | 2014-12-17: TBD
6 | TBD | T-t | New/Revised Edition | T-T Risk Management & Insurance, 2nd Edition |  |  |  |  | Simple | jason - P&C to be assigned inside |  |  |  |  | 2014-12-17: TBD
Under Discussion | [21 empty] | Comments
6 | 2770011 | T-T | New Edition | Tools & Techniques of Financial Planning, 11th Edition |  |  |  |  | Simple | [12 empty] | awaiting financials
|  |  | 200 | Supplement/companion to SS/Medicare Facts | [17 empty] | target 12/14
|  |  | 350 | State Specific Tax Facts Supplement | [17 empty] | Cline investigating
|  |  | Online | Retirement Plan Service/partner with Advisys | [5 empty] | rick - protptype 4/22 | [11 empty] | Aim to release in July
|  |  |  | COBRA Facts | [17 empty] | Rick K.
|  |  |  | FCSL Case Law Digest | [17 empty] | December 2015?
Other Projects
Tier IV FC&S
|  |  |  | Adding case law to FCSL and FCIN | Begin 10/13